## Slide 1: ISS Astrobee Facility
Sponsoring Org/Office Code: ISS Program, OZ3
Name of Forum: Astrobee Working Group June 2023
Date: June 1st, 2023
Jose V. Benavides
NASA Ames Research Center
Intelligent Systems Division (Code TI)
Henry Orosco
ISS Research Portfolio Manager

## Slide 2
Purpose
Purpose: Provide Astrobee Facility overview, status and near-term plan
Select the appropriate box below:
  □ Request for Technical Concurrence
  Information Only
  □ Management Direction
  □ Response to an Action Item
Agenda:
  Overview
  Facility Status
  Engineering
  Operations

## Slide 3: Agenda

## Slide 4: Overview

## Slide 5: Project Description
Based at Nasa Ames Research Center, the ISS Astrobee Facility provides a free-flying robotic system for ISS research and ISS STEM outreach. The Astrobee free-flying robotic system consists of three cubed-shaped robots, software, and a docking station used for recharging. The project provides sustaining engineering tasks for ensuring the facility operational readiness on ISS. The project provides payload support to users from academia, private industry, NASA, and other government agencies in the execution of ISS approved research and STEM objectives.
Chris Cassidy, GMT 248 2020

## Slide 6: Astrobee Facility Overview
Astrobee research platform ecosystem
  Astrobee hardware: Ground and flight units
  Ames Research Center Experimental Facilities
  Astrobee Robot Software
  Access to the International Space Station
Support different research: Artificial Intelligence, manipulation, computer vision, Human Robotic Interactions, many, many other fields!

## Slide 7: Astrobee Working Group Community
Astrobee Working Group (AWG) meeting
  Meet twice a year (ideally in-person)
  Timed similarly to the POIWG conference
  Next: Fall 2023
Purpose:
  Information sharing across the Astrobee community
  Astrobee Facility shares status, updates, overall calendar
  Discuss proposed changes/updates

## Slide 8: Pictures from last AWG
November 11th, 2022, Astrobee Working Group

## Slide 9: Astrobee Summary since last AWG

## Slide 10: Astrobee 12-month forward plan

## Slide 11: Facility Status

## Slide 12: Hardware and Lab Status
  Granite Lab: Online
  Flight Lab: Online
  Engineering Evaluation Lab (EEL): Available upon request
Name | Status
Flat Sat A | Operational
Flight 1 (Bumble), Flight 3 (Queen) | In Space, Operational
Flight 2 (Honey) | On Ground, Ready
Flight Spare | Operational
Cert (B#) | Operational
Ground (Wannabee) | Operational

## Slide 13: Honey Repair
SD card was configured
New SD card replaced LLP, MLP, and HLP SD cards
  Successful replacement of SD cards
Performed (ground) Honey Checkout
  Successful checkout complete
Next Steps:
  Ready to ship if needed anytime in the near future

## Slide 14: Astrobee Ops Room
Converted MGTF to Astrobee Ops room/ support ISS activities
Replicate previous ops room(MMOC)
Current status:
  Computers are up and running
  Running operations software
    IVODs, VLC, Putty, HOSC VPN Client, etc.
  Future work
    Installing astrobee GDS, git repository
    End to end testing

## Slide 15
On 10-11-22, during the prep activity for the Kibo RPC Finals 3, the dock processor presented multiple read-only errors.
After crew performed a power cycle, the Dock Processor restarted into rescue mode.
The Dock controller is unaffected – still able to charge Astrobee’s batteries.
Attempt to recover the Dock Processor remotely was unsuccessful.
New, more robust SD cards are being setup and prepared for launch to replace the corrupted one on the Dock
I2C
I2C
I2C
Rescue mode:
very limited functionalities
Dock Controller
Dock Processor
AB2
Nominal functionalities:
Charging AB batteries
AB1
ISS Dock Station: Status

## Slide 16: Ubuntu 20.04 Transition
Current status
  All Ubuntu 20 images operational (root, rescue, custom)
  All FSW products (Astrobee debians) ready for Ubuntu 20 armhf
  First official FSW release supporting Ubuntu 20 armhf available (0.17.0)
  FSW 0.17.0 installed to ground unit (wannabee) and tested since February 17th
Next Steps
  Continue image and FSW testing.
  Documentation
  Prepare deployment to ISS (procedures, testing, approvals)

## Slide 17: Coverage Analysis
Software tool helps visualize the coverage of a given map or Astrobee trajectory
Coverage of a map: the number of ML features in a volume of along an imaginary grid on the overhead, aft, forward, deck walls and the front of the airlock throughout the JEM
Coverage of an Astrobee trajectory: the number of ML features the robot registered at a given pose of the trajectory.
The more ML features, the more stable Astrobee localization will be.
Three possible outputs:
  3D JEM heat map
  3D Astrobee trajectory heat map
  PDF report

## Slide 18
Chart: Localized Images from Std Trajectory (%)
| CM-S7 | CM-S8 | CM-S09 | CM-S10
dali | 23.5417 | 17.5 | 40.0227 | 21.2583
eisen | 24.6875 | 16.1207 | 36.1678 | 21.5443
goya | 33.0208 | 21.8103 | 46.5986 | 22.2116
hamilton | 65.625 | 31.6379 | 62.585 | 22.6883
Astrobee Facility requires a method to determine when a new map or update should be done
Standard Trajectory: Large image collection trajectory performed at every Crew Minimal activity.
Only portion from dock to face airlock to move backwards to Bay 1.
Historical data is compared across multiple maps
When current map has <10% localized images than previous one, update/new map required
Map Update Decision Tool

## Slide 19: File Checksum
Background:
  On 05/02, an Astrobee Facility error resulted in the installation of an outdated version of the APK.
  The updated file had fixes implemented during granite lab testing of the previous APK.
  About 15 minutes of testing time were used to diagnose and correct the issue.
Process Change:
  Previously checksums of files were requested from Guest Scientists as good practice
  Checksums will now be required for all software deliveries
  Checksums will be added as an item to review during the TRR

## Slide 20: Operations: Functions
Ensure Facility Readiness for ISS Test Sessions
  All crew training is handled via Onboard Training (OBT).
  Manage crew procedure and all planning products updates via OCR/ECR system
  Coordinate crew time with ISS Lead Increment Scientist and POIC Cadre
  Assist Astrobee team & PDs in acquiring proper access to ops systems as required for real-time ops support
  Coordinate with investigators for product development and delivery
  Help investigators set up remote communication capabilities as needed
Real-Time ISS Test Session support
  Coordinate with MSFC and POIS (POIC Specialist) all deltas to real-time ops and products
  Support crew & POIC cadre with real-time ops – plan and conduct crew conferences as needed
  Coordinate commanding and data download window requirements and planning
  Test session data and video management
  Real-time commanding support
Public Relations
  Maintain website, work with ARC PAO office to publish material on site

## Slide 21: Operations: Functions
Increment Planning
  2-pager development and submittal, updates as needed throughout increment
  Assist PIM (Payload Integration Manager) with CEF inputs as needed
  Regular timeline planning with Lead PPM (Payload Planning Manager), PPM planning team and MSFC POIS/PARC team
Safety and Verification Assessments
  Integrated Safety & Verification Assessments as needed for Astrobee Facility and Guest Science Payload Developers (PDs)
  Continued SPHERES Safety & Verification focuses on return of hardware.
  Complete CoFR (Certification of Flight Readiness) for ground systems and on-orbit hardware and operations products
Astrobee Ground Ops Development
  Coordinate ground Engineering and Operations Readiness Tests (ERTs/ORTs) in preparation for real-time ops
  Work with Astrobee team and PDs to develop flight procedures, coordinate reviews with MSFC for final delivery and formal ECR review

## Slide 22: Ops Stats
From the last AWG (11.10.22) to date
  8 Test Sessions over 33 weeks (1+ Test Session/month)
  3 unique crew (~9 crew hours total)
  ~70 real-time console ops hours (not including data downloading etc.)
Fiscal year (Oct 2022 through May 2023) to date
  12 Test Sessions (1.5 Test Sessions/month)
  5 unique crew (~20 crew hours total)
  ~90 real-time console ops hours (not including data downloading etc.)
From 4/30/20 (our first remote ops Test Session) to date
  97 (of 139 total – 70%) remote Test Sessions (2.6 remote Test Sessions/month)
  23 unique crew (~200 crew hours total)
  ~800 real-time console ops hours (not including data downloading etc.)
From Dock Install and Checkout (February 11, 2019) to date
  139 Test Sessions (2.7 Test Sessions/month)
  29 unique crew (~230 crew hours total)
  ~1000 real-time console ops hours (not including data downloading etc.)

## Slide 23: On-Orbit Activities (since 11.10.22)
AB132: Crew Minimal S9 February 3, 2023
AB133: SoundSee Science 4 Repeat February 16
AB134: Astrobatics Science 4 February 23
AB135: Crew Minimal S10 March 10
AB136: Zero Robotics Tech Demo 1 March 24
AB137: Zero Robotics Tech Demo 2 May 2
AB138: UAE Zero Robotics Dry Run May 16
AB139: Kibo RPC4 Technical Rehearsal 1 May 30

## Slide 24
Milestone | Deadline
PD inputs (procedures, planning products, Flight Rules, PL Regs) | L-12 weeks Launch Date/Vehicle (T)
Pre-ECR Submit | Count back from ECR submittal, depending on 1 or 2 week ECR review
ECR Submit | L-6 weeks (for 2-week Impact review) L-5 weeks (for 1-week review)
Team ECR Review | L-4 weeks (week prior to IMEP with at least 2 days for comment verification)
Board at IMEP (Mondays) | L-3 weeks (or Ops-3 weeks)
PL Reg/Flight Rule/OBT/Phase III Self Study Baseline | Ops-1 week Note: more commonly, Self Study is baselined same time as crew procedures
Ops Deliverables/Planning – MSFC

## Slide 25: Ops Deliverables/Planning – Astrobee Internal
Milestone | Nominal
ISS OPS (ERD+>1week) Estimated Readiness Date (ERD) | ERD = MSFC Baseline of Ops/Flight Products Launch Date/Vehicle (T)
Paper SIM (pre-ECR) | ERD - 7 weeks
Paper SIM if needed (pre-OCR) | ISS OPS - 3 week
PD connectivity test complete | ISS OPS - 2 weeks
PD software delivery (APK, Debian(s), etc.) | ISS OPS - 2 weeks
Ground procedure complete | ISS OPS - 2 weeks
Rehearsal ORT (Operations Readiness Test) | ISS OPS - 1 week
TRR (Test Readiness Review) | ISS OPS - 1-4 days
ARC completes working draft of Ops Products | ERD - 6 weeks
PD submission of planning inputs | ERD - 10 weeks
OPS Products Updates | ISS OPS - 2 weeks
Software (list needed for OCR) | ISS OPS - 2 weeks

## Slide 26: Crew Procedures & Safety Status
SAFETY
Integrated Safety Data Package for Astrobee-Clingers – Submitted 2023-02-08
CREW PROCEDURES
Baselined
  Astrobatics - Science 4
  SoundSee - Data Collection 4 [Repeat]
  Zero Robotics - Tech Demo 1 and Tech Demo 2
  JAXAs Kibo RPC-4 Tech Rehearsal 1
    Review of crew procedure developed by JAXA
Ready for ECR process for baseline
  Clingers (crew procedures for main activity and software upload)
Updated
  Astrobee Perching Arm Installation
  Astrobee Perching Arm REMOVAL
  Astrobee Free Flyer Power On
  Astrobee Free Flyer Power On with No Dock Power Cycle
  Astrobee JEM Prep
Upcoming
  Astrobatics Science 5

## Slide 27: Astrobee on Social Media
Website
  http://www.nasa.gov/astrobee
We are in the process of transitioning to a new Content Management System which will result to new Astrobee webpage layouts by the end of July 2023.

## Slide 28
QUESTIONS?

## Slide 29
On Break, back at 01:45pm CST