## Slide 1: ISS Payload Integration Introduction for Payload Developers aka PIM Roadshow
Version Date: May 24, 2023

## Slide 2: Payload Integration Manager (PIM)
I am your Payload Integration Manager - your PIM
I am here to help you and your team. I am your primary point of contact and your guide on this integration journey.
My job is to also ensure the safe launch, integration, operation, and data return for your payload
I will build you an integration schedule to keep you on track as we approach key milestones and reviews
I will facilitate PIM Tag-Ups including you and the integration team to keep us all in sync
Now let’s introduce you to your integration team!

## Slide 3: Payload Integration Team
An integration team will be assigned based on the specific needs of your payload
  The composition of the integration team is determined by the number and type of interfaces the payload needs for transport (ascent/descent) and on-orbit
  The “Usual Suspects” will include:
    PIM – That’s me
    RPM (Research Portfolio Manager) – Odds are you already know your RPM as they helped you and your sponsor get approved to begin integration activities. They will also help the PIM resolve any issues that may arise.
    SPE (Safety Panel Engineer) – Supports execution of the safety review plan to identify and verify hazard controls
    PIRE (Payload Interface Requirements Engineer) – Defines interface requirements for transport and on-orbit interfaces as part of the interface verification process
    POI Specialist – Supports definition of ops products inputs for on-orbit procedure development
    PARC (Payload Activity Requirements Coordinator) - Develops planning products based on crew time and activity requirements needs
Other variables that determine integration team members include:
  Software and telemetry needs
  On-orbit topology
The integration team ensures that your payload is safe to operate for its entire lifecycle, including disposal
PD
PARC
SPE
PIRE
POI
Specialist
PIM/RPM
Notes: Integration Team Definition
  The group of individuals assigned to ensure a payload completes all requirements (operations, safety, interface, etc.) and is ready to be flown, operated or conducted onboard ISS
  This team is comprised of many members
    The Payload Integration Manager (PIM)
      Is the team focal point and facilitates communication and integration between the various team members
Payload Data Integrator (PDI)
  Populate and propagate data into multiple ISS Program databases on behalf of the PD
  Perform the initial data entry allowing the PD to provide the required data in any format
    Provides the propagation, management, and validation of data into other databases after initial entry
  Works closely with the PIM throughout integration to provide reliable and timely data entry support to the PD
Research Integration Manager (RIM)
  Work official NASA contractual agreements
    Provide NASA level concurrence
    Aid PD in Physical and IT Resource Access
  Primary Payload interface to OZ Management
    Help coordinate Non-OZ resources to facilitate integration
  Perform Pre-Integrated Payload List (IPL) PD integration

## Slide 4: Payload Integration Team (cont.)
  Never Fear – remember your PIM is your primary POC and will help you with everyone on the integration team!
Who else is working for you besides the “usual suspects”?
  Topology Rep – assesses deployment locations of your payload
  Cold Stowage – provides controlled/conditioned environments for all phases of flight if required
  FPMs (Flight Payload Managers) – ensures you get manifested and coordinate turnover dates
  PDI (Payload Data Integrator) - Populates, manages, and validates duplicate data in all applicable ISS Program payload databases
  Manifest – Implement manifesting data into MIDAS
  CMC (Cargo Mission Contract) – packs your hardware for launch
  Engineering Disciplines – Structures, Thermal, C&DH, EME, etc., – reviews verification submittals
  HFIT (Human Factor Integration Team) – helps with human factors verification
  (PSIE) Payload Software Integration Engineer –ensures your software is ready
  Get the idea? Lots of folks working to make you successful
PD
PARC
SPE
PIRE
POI
Specialist
PIM/RPM
HFIT
FPM
TOPO
CMC
PDI
Manifest
Cold Stow
PSIE
Eng. Discp.

## Slide 5
The Science, Technology, and Exploration Flow
or simply “The ST&E Flow”
aka…The ISS Payload Integration Process

## Slide 6: ST&E Integration Flow Phases
The ST&E Flow is a 6 phase integration flow modeled after standard NASA systems engineering development processes
The flow is flexible - not every milestone in the flow is executed for every payload
The PD defines their development schedule – the Program defines the integration schedule in accordance with the PD’s development schedule
The Program targets a flight based initially on the readiness date provided by the PD and any specific business considerations
Actual flight assignment is done approximately half way through the flow, taking into consideration payload readiness and its overall risk (risk to the PD and/or risk to the Program) in conjunction with the sponsor
Transition between the phases is internal to the ISS Program to assess and mitigate risk
Conception
Plan and Prepare
Design and Analyze
Verify
Deliver
Operate & Post Operations
Notes: As we move through this process, the transitions between phases should be transparent to you. These are markers to ensure we are meeting the required milestones in each phase.

## Slide 7: ST&E Integration Flow Phases
The purpose of the Conception Phase is for the Program to: a) understand what the PD needs from the ISS Program by learning about your payload; b) establish the Programmatic agreements necessary to enable successful operation.
A Kickoff meeting is scheduled to learn about the payload
  What is the payload? What does it need from the launch vehicle and the ISS?
  What is the concept of operations?
  What is the development schedule? Are there design reviews?
  Is a bridge team needed?
Complete the Payload Integration Agreement (PIA)
    The PIA between the PD & the ISSP as prepared by the PIM
Based on the payload Kickoff data and PIA, the specific integration team is defined and the initial integration schedule is built
Identify/Mitigate Risk
Conception
Plan and Prepare
Design and Analyze
Verify
Deliver
Operate & Post Operations
Notes:   Have a kickoff…explain what info we need and what we need to know about the payload. Are design reviews planned, etc.
  Discuss bridge team options.
    We can provide specific expertise various disciplines if needed.
  Generate a PIA/Add to User’s List.
    Explain the purpose of the PIA
  PIM builds integration schedule with all the key milestones to keep the PD on track and the Program informed of progress.

## Slide 8: ST&E Integration Flow Phases
Conception
Plan and Prepare
Design and Analyze
Verify
Deliver
Operate & Post Operations
The primary purpose of the Plan and Prepare phase is for the ISSP to collaborate with the PD to provide items required to design the experiment or payload. We will:
  Define transport interface requirements
  Define on-orbit interface requirements
  Conduct a Safety Review (Phase I) to determine hazards and define control requirements
Initiate Research Planning
  Crew Time Phasing Data
  Research Planning Data
Determine Preliminary Topology
Identify/Mitigate Risk

## Slide 9: ST&E Integration Flow Phases
Design and Analyze
Conception
Plan and Prepare
Verify
Deliver
Operate & Post Operations
The primary purpose of the Design and Analyze phase is to conduct design reviews to understand maturity of design and forward risk as the integration process moves into fabrication & verification.
This phase typically begins with a Preliminary Design Review and concludes with a Critical Design Review
Complete a Phase II Safety Review
This phase is the most frequently tailored phase since the majority of PDs do not have formal design reviews
Flight assignment and manifesting
Determine final topology
Define test plan for verification
Provide inputs for operations products
Identify/Mitigate Risk
Notes:   ISF (Investigation Summary Form) will be requested – briefly explain this.
  Part level manifest data will be provided.
  Safety will check design for hazard control compliance.
  Final topology.
  Crew procedure inputs will be provided.
  Software test products will be provided.

## Slide 10: ST&E Integration Flow Phases
Design and Analyze
Conception
Plan and Prepare
Verify
Deliver
Operate & Post Operations
The primary purpose of the Verify phase is to ensure fabrication & complete verification in preparation for shipment and launch vehicle integration. During this phase we:
  Submit interface verification and obtain approval
  Complete a Phase III Safety Review, submit safety verification and obtain approval
  Provide data for ground handling and launch vehicle integration
  Prepare hardware for turnover
  Identify/Mitigate Risk

## Slide 11: ST&E Integration Flow Phases
The primary purpose of the Deliver phase is to perform launch vehicle integration and deliver your payload to ISS to fly. We will:
  Deliver All:
    Hardware, Software, Safety, Verification, Training Products and Operational Products (Ground & Crew)
  Deliver your payload to CMC for packing, final time critical payload preparation and delivery
  Launch YOUR Payload to the International Space Station
Design and Analyze
Conception
Plan and Prepare
Verify
Deliver
Operate & Post Operations
Your payload is in there!

## Slide 12: ST&E Integration Flow Phases
The primary purpose of the Operate and Post Operations is to operate the experiment (i.e. perform your science and get you your data) and complete your post ops integration.
After Operations
  Payload Hardware will be returned or discarded
Now let’s go get your next payload ready to go!
Design and Analyze
Conception
Plan and Prepare
Verify
Deliver
Operate & Post Operations
Your payload on the ISS
Your samples are in there!

## Slide 13
Badging, IT Access
&
Electronic Accounts
Overview

## Slide 14: Badging & IT Access – U.S. Citizens & Foreign Nationals
PD team must request Badging & IT Access for all necessary team members, including Foreign National (FN) team members
Standard Time for Approval:
  U.S. Citizens
    Approximately 7-14 days, depending on requests details
  Foreign Nationals
    Approximately 3-4 weeks for non-designated country FNs, depending on the requests details
    Approximately 30-180 days for designated country FNs, depending on the requests details

## Slide 15
ORBIT (OZ Requirements Baseline and Integration Tool)
  Simplified access to the various NASA mission planning tools, one-time entry of payload data into these tools, and ease of navigation through the various mission planning organizations
IHS (ISS Hazard (Safety))
  Used for hardware provider submittal, ISS Program review and approval, and reference/utilization of safety data across the ISS Program
EDMS (Electronic Document Management System)
  ISS EDMS is the International Space Station (ISS) repository for ISS Program documents
CMC (Cargo Management Contract) Tool - Access portal to other applications such as:
  eLRODS/eRMDP (electronic Launch, Return and On-Orbit Data Set / Return Manifest Disposition Plan)
    How is your payload and associated equipment to be handled, packed, launched and returned
  eLabel (electronic Label Generation Requests)
  RFS (Request for Support)
IT Access & Electronic Accounts

## Slide 16
Payload Data Integrator (PDI) Services
Roles and Responsibilities
  Payload Developer (PD):
    Provides data once and in any format you choose (Word, Excel, PowerPoint, verbally, email, etc) within a timeframe designated by the PIM schedule
  Payload Integration Manager (PIM):
    Functions as a liaison between PD and PDI to ensure that information is provided to the PDI in a timely manner and verifies data entered into databases prior to submittal
  Payload Data Integrator (PDI):
    Populates, manages, and validates duplicate data in all applicable ISS Program payload databases
Don’t feel overwhelmed by the data entry requirements or tools! We are here to help!
I will work closely with the PDI throughout the integration process to provide reliable and timely support to all PD teams.
  PDI will attend the kick-offs and PIM Tag-ups
  We will ensure that the data is entered correctly prior to submittal

## Slide 17
Intellectual Property & Proprietary Information
(Data Handling)

## Slide 18: PD Proprietary Data
All PD provided data is considered sensitive
  Controls are in place to limit data exposure to only individuals with applicable work scope (i.e., those who need to know)
Data that is marked as proprietary by the PD has additional controls
  Program databases protect and segregate the data
  One PD is not able to see another PD’s data
The PD is responsible for determining if their data is proprietary and marking accordingly
PD should note that proprietary data has limitations on how data can be shared and transferred to integration team members and may result in increased integration processing time as well as reduced operation time.
  General guidance is on the next 2 pages
The ISS Integration team consists of multiple civil servants and contractors that are legally REQUIRED to honor proprietary data markings. As specified in our contracts:
  Use data only for the purpose necessary to integrate your payload and get you your data
  Safeguard data from unauthorized use and disclosure
  Allow access only to those with a “Need to Know”
  Not to release outside of the organization
  Train our workforce on the proper handling of proprietary sensitive information

## Slide 19
Proprietary markings drive significant work for NASA civil servants and contractor team members in order to properly protect the data. It is critical that you mark only what absolutely needs to be marked as proprietary – mismarking will add delays in processing your data.
What is proprietary/sensitive data?
  Information (data or other products) that is not in the public domain; information that a contractor has developed at private expense that has actual or potential economic value: computer code/algorithms, engineering drawings, analyses, manufacturing processes, design specifications, test results.
What is not proprietary/sensitive data?
  Information that is currently in the public domain: publications, presentations, websites, open source software. Note: This list is not intended to be comprehensive. When in doubt, ask your company legal representative.
Your organization needs to tell NASA if your data is propriety data or not.
  Be aware of the markings on all your data
  Be aware that using standard templates/standard markings may not accurately reflect the actual data contained within (a very common problem)
Proprietary Data Guidance

## Slide 20: Proprietary Data Guidance (cont.)
Transfer of Payload Developer Proprietary Data
Preferred method: NASA Systems on Secure NASA Servers
  ORBIT, NASA SharePoint or EDMS
Email should NEVER be used for transmission of PD Proprietary data
  The only exception is to address a critical data exchange when no other means are available
    Critical would typically be defined to address an on-orbit anomaly to address crew safety
Be careful of disseminating hard copy Payload Developer proprietary data.
  Better to upload it to the appropriate NASA Database or Application
Your PIM will guide you on how to exchange proprietary data via the proper methods
Remember that the exchange methods and our job in general includes protection of your proprietary data

## Slide 21
Payload Developer Submittal Expectations

## Slide 22: PD Submittal Expectations
Defines when you are required to submit final products based on the cargo type (s) and research timing needs
The Program teams need sufficient time to:
  Assess manifest request & mission priorities for accommodations
  Review and approve verification and safety submittals
  Pack and integrate hardware into the launch vehicles
  Ready operations products
The timing of these submission dates are determined by multiple factors:
  Does your payload have time critical elements necessitating a turnover closer to launch?
  Does your payload have limited life items necessitating early on-orbit operations or other scheduling constraints?
  Can your payload be operated when on-orbit resources are available – flexible scheduling?

## Slide 23
Expectations Generic Flight Milestones (Chart)
Launch
Manifest Request & Mission Priorities Snapshot
L-20 W
Manifest Request & Mission Priorities Final
L-16 W
Mission Accommodations Finalized
L-12 W
24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Regular Cargo Turnover to CMC
L-9.5 W for Dragon L-10.5 W for Cygnus
POWR
L-5 W
OZ CoFR
L-4 W
SORR
L-3 W
Time-Critical Turnovers
Unpressurized Cargo Turnover
Varies by vehicle
Pre-Turnover Manifest Validation for Regular Cargo
T/O to CMC-1 week
Pre-Turnover Manifest Validation For Time-Critical Cargo & Return Manifest Validation
POWR-1 week
Science Verification Confidence Assessment
L-16 W
Increment Activities & Mission Constraints Validation
L-12 W
10
11
12
9
13
1
2
4
3
7
5
6
8
L- Weeks

## Slide 24: Submittal Expectations: Pressurized Cargo Turnover
Regular Cargo Turnover is for any payload that does not require late processing due to time critical needs
  Hardware is turned over to Cargo Mission Contract (CMC) personnel to be packed for flight
Time Critical Cargo Turnovers are understood to have limited life items (biological, temperature sensitive/cold stowage), powered lockers, or a science need for a later turnover
  Hardware is turned over directly to the launch site to CMC or Cold Stowage per a pre-coordinated schedule. From there, CMC/Cold Stowage turns hardware over to the launch vehicle.
SpaceX Dragon |  |  | Northrup Grumman Cygnus |  |  | JAXA HTV
Regular Cargo Turnover | Time Critical Cargo Turnover |  | Regular Cargo Turnover | Time Critical Cargo Turnover |  | Regular Cargo Turnover
CRS2 |  | CRS2 | CRS2 |  | CRS2 | 
L - 9.5 Weeks | Ambient | L - 30 Days | L - 9.5 Weeks | Ambient | L - 30 Days | L - 6.5 Months
 |  | L - 5 Days |  |  | L - 5 Days | 
 |  | L - 36 Hours |  |  | L - 36 Hours | 
 | Conditioned | L - 4 Days |  | Conditioned | L - 4 Days | 
 |  | L - 3 Days |  |  | L - 3 Days | 
 | Powered | L - 25 Hours |  | Powered | L - 24 Hours | 

## Slide 25: Submittal Expectations: Unpressurized Cargo Turnover
Unpressurized Turnover Payloads: Payloads mounted on the exterior of the transport vehicle or in the unpressurized trunk.
SpaceX Dragon | SNC | JAXA HTV-X
Unpressurized Cargo Turnover direct to visiting vehicle provider |  | 
L-32 days (L-45 days if direct mount) | L-30 days (L-TBD if direct mount) | L-10 weeks (L-TBD if direct mount)
Full Safety is approved before turnover.
  The Phase III Safety Review or OSB review must be scheduled before turnover allowing time to address Phase III actions.
  Safety data packages and required safety forms must be submitted 20 business days prior to the scheduled review.
Transportation and on-orbit interface verification is approved before turnover
  Transport and On-Orbit interfaces with test or analysis verification submittals are all due No Later Than (NLT) 21 days before turnover.
  Requirements with CoC verification submittals are due before turnover (no need for 21-day review).

## Slide 26: Payload Integration Team Members
  RPM - Research Portfolio Manager: POC for NASA Research authorization, funding agreements, research objective definition, Space Act Agreements
  PIRE - Payload Interface Requirements Engineer: Works with the PD to identify the ISS-to-Payload interface requirements and document them in an IRB - Interface Requirements Baseline
  PSIE - Payload Software Integration Engineer: Supports payload S/W development, unique S/W requirements, S/W testing, and data/media submittals
  SPE - Safety Panel Engineer: Assists the PD by explaining the ISS Safety process/ policies, identifying unique payload Hazards and coordinating Safety meetings
  PIE - Customer Support Team Representative: From the HOSC - Huntsville Operations Support Center assists the PD with defining, documenting, and implementing their GDS - Ground Data Services requirements and coordinates training for POIC - Payload Operations Integration Center
  POI Specialist - POC for Op Nom, flight crew procedures, flight crew training, GSP - Ground Support Personnel training, and overall POC for POIF - Payload Operations Integration Function activities
  PARC - Payload Activity Requirements Coordinator: Works with the PD to develop flight crew operational plans and planning models
  PSO - Program Science Office: Communicates science goals and results to science community
  HFIT - Human Factors Integration Team / IPLAT - ISS Payload Label Approval Team engineer: Supports the PD with verification of flight crew interface requirements, and Label design, development, and verifies labels meet requirements.
  FOD – Flight Operations Directorate: Crew Office Representative supports the PD with Astronaut Office operational perspective, best practices and lessons learned
  Robotics Engineer identifies requirements and coordinates needed robotic assessments and operations (external payloads only)

## Slide 27: Acronyms & Terms NASA’s Acronym Database: http://www6.jsc.nasa.gov/AcronymCentral/scripts/searchresults.cfm
ATV - Automated Transfer Vehicle
AWG - Acoustics Working Group
C&DH - Command and Data Handling
CDR - Critical Design Review
CEF – Change Evaluation Form
CETI - CEF Tracking & Integration (tool)
CMC – Cargo Mission Contract
CoFR - Certification of Flight Readiness
DMS - Data Management System
DS - Data Set
EDMS - Electronic Data Management System
EEE - Electrical, Electronic, and Electromechanical
eRCAR - ExPRESS RCAR
ERDB – Export Record Database
ExPRESS - Expedite the Processing of Experiments to Space Station
FLT - Flight
GDS - Ground Data Services
GLC – Guidelines and Constraints
GSRP - Ground Safety Review Panel
H/W - Hardware
HFIT - Human Factors Integration Team
HOSC - Huntsville Operations Support Center
HTV-IIA - JAXA launch vehicle
ICD - Interface Control Document
IDD - Interface Definition Document
IdMAX - Identity & Access Management Tools
IDP - Integration Data Pack
I - # Increment minus (month or day )
Inc - Increment
IP - Internet Protocol
IP - International Partner
IPLAT - ISS Payload Label Approval Team
IRB - Interface Requirements Baseline
IRD – Interface Requirements Document
ISS - International Space Station
JSC - Johnson Space Center
KSC - Kennedy Space Center
L-# - Launch minus (month or day)
eLRODS - Launch / Return / On-orbit Data Set
MIOCB – Mission Integration Operations Control Board
MR – Manifest Request
MRICB - Multilateral Research Integration Control Board
MSFC - Marshall Space Flight Center
NAMS - NASA Account Management System
NDC - NASA Directory Consolidation
NOMAD – NASA Operational Messaging and Directory Service
NPOCB - NASA Payload Operations Control Board
NSTS - National Space Transportation System
OpNom - Operations Nomenclature
ORBIT - OZ Requirements Baseline & Integration Tool
ORBS – ORBIT Schedules
OWTL - Open Work Tracking Log
PARC - Payload Activity Requirements Coordinator
PD - Payload Developer
PDI – Payload Data Integrator
PDL - Payload Data Library
PDR - Preliminary Design Review
PIA - Payload Integration Agreement
PIM - Payload Integration Manager
PIMS - Payload Information Management System
PIP - Payload Integration Panel
PIRN - Payload Interface Revision Notice
PITA - Payload Integration Agreement Database
PMIT - Payload Mission Integration Team
PODF - Payload Operations Data File
POIC - Payload Operations Integration Center
POIF - Payload Operations Integration Function
POIWG - Payload Operations Integration Working Group
PSCP - Payload Software Control Panel
PSRD - Payload Support Requirements Document
PSRP - Payload Safety Review Panel
PTP - Payload Tactical Plan
PVP - Payload Verification Plan
RAPTR - Remote Advanced Payload Test Rig
RCAR - Requirements Change Assessment Report
RICB - Research Integration Control Board
RIFD - Research Investigation and Facility Database
RPM – Research Portfolio Manager
RMDP – Return Manifest Dispositioning Plan
RPO - Research Planning Office
RPWG - Research Planning Working Group
RVCP - Requirements and Verification Control Panel
S/W - Software
SAA – Space Act Agreement
SAR - System Acceptance Review
SDP – Safety Data Package
SPE – Safety Panel Engineer
SPIA - Standard Payload Integration Agreement
SPIP - Station Program Implementation Plan
SR&QA - Safety Requirements and Quality Assurance
SRR – Systems Requirements Review
TGHR – Time-Critical Ground Handling Requirements
TICB – Transportation Integration Control Board
TIM - Technical Interchange Meeting
TReK - Telescience Resource Kit
US PODFCB - US Payload Operations Data File Control Board
User-ID - User-identification
VERITAS - Verification of Engineering Requirements Interface for Tracking, Approval and Submission tool
VITT – Vehicle Integration Test Team
VPN - Virtual Private Network

## Slide 28: Points of Contact
  PIM - Group Lead
  Melissa Boyer
  Melissa.L.Boyer@boeing.com
  (832) 205-4817
  PIM – Group Lead | Roadshow POC
  Mo Nguyen
  Mo.Nguyen@boeing.com
  (832) 985-9555