## Slide 1
PIM Update

## Slide 2: PIM Status
  What integration work has been accomplished since last SPHERES Quarterly Working Group on 05/04/2017?
  SPHERES Tether Slosh – targeting Inc. 53/54 for launch
    Hardware readiness is mid-September
    Safety Phase I/II SDP completed on 07/12/17
    Safety Phase III SDP and integrated SDP submitted on 08/04/17, ECD: 9/1/17
    All payload requirements submitted ; waiting on change paper approval
    Hardware labels in work
    Initial procedure inputs provided; need to provide additional updates/inputs
  SmoothNav – First session targeted for end of year
    No hardware; software only; will use existing Vertigo/SPHERES hardware on-orbit
    Total of 4-5 test sessions : 1st test session scheduled for the end of this year
    Kickoff meeting completed on 08/17/17
    Payload Integration Agreement (PIA) in work; change paper to be submitted to request test sessions

## Slide 3
  RINGS – launched on Flight HTV-4 (08/03/13)
    RINGS hardware [RINGS hardware, battery chargers (qty. 2), and DeWalt batteries (qty. 16)] to return on SpX-12: TBD – most likely will need to be manifested for return on another flight
    8 Dewalt batteries to remain on-board: TBD
  SPHERES Halo - launched on Flight SpX-8 (04/08/16)
    Five test sessions planned in Increment 51/52 (04/15/17- 09/02/17)
      TS #1: Blue Checkout and Halo Checkout: occurred on 02/02/17
      TS #2: Halo Checkout: occurred on 02/03/17
      TS #3: Halo Science 1: 5/29/17-5/30/17
      TS #4: Halo Science 2: 6/23/17
  SPHERES Zero Robotics:
      Inc. 51/52 (04/10/17-09/05/17): 2 sessions completed; Dry run completed on 8/4; ZR finals completed on 8/11
  Slosh Coating – was manifested on Flight OA-7 (02/17/16)
      Hardware was damaged when stowed in Cgynus vehicle; removed from the flight; ISS lesson learned presentations on-going
      Will remanufacture tanks and fly at a later TBD date
PIM Status--continued

## Slide 4: PIM Status--continued
  SPHERES Consumables - multiple flights
    Flight 67P (06/14/17)
      Qty. 4 grey tanks launched
    Flight SpX-12:
      Qty. 11 grey tanks launched (08/14/17)
      Qty. 13 grey tanks to return on SpX-12 (09/17/17)
    Pink tanks—Flight TBD
  Other information:
    SPHERES Beacon will launch on Flight OA-8 (11/10/17)

## Slide 5: ISS Flight Plan (in-work version as of 08/17/17)