## Slide 1
Astrobee PIM Update

## Slide 2: Current integration work
  Docking Station targeting OA-10 launch (11/17/18)
    Phase III Safety Review completed in December 2017; close out after environmental testing (August)
    Docking Station is in MIDAS Prime; bracket hardware and on-orbit spares need to be added
    Two sets of labels have been received; third set is in work
    Location in JEM accepted by JAXA in Jan 2018; PIRN in work to document I/F requirements
    An agreement with the HOSC for video routing was approved in PIA Rev. D (May 2018)
    Discussion with the Imagery Working Group will be held in late summer to discuss video routing
    PIA Rev.E in work; makes PIA a facility PIA and adds Port Tester
    Initial installation procedures required by 8/21/18
    Initial planning inputs to PARC required by 9/19/18
    OBT product delivery required by 10/5/18
    JSL/SDIL end-to-end testing was scheduled for Sept.; however, it may be delayed
    Hardware delivery scheduled for 9/20/18
  Two Astrobee Free Flyers targeting SpX-17 (2/01/19)
    Hardware delivery scheduled for 11/30/18
  One Astrobee Free Flyer targeting OA-11 (4/17/19)
    Hardware delivery scheduled for 1/16/19

## Slide 3: ISS Flight Plan (in-work version as of 06/18/18)