## Slide 1
SmoothNav

## Slide 2: SmoothNav Overview
Objectives
​[ISS] Smoothing-based software for incremental estimation of the relative poses and velocities between multiple small spacecraft.
  Overcomes the limitations presented by a filtering framework:
    varying number of operating agents and sensors,
    distinct sampling frequencies,
    robustness against satellite and sensor failures.
  Software-only ISS investigation using existing VERTIGO hardware & procedures
​[Ground] Long range depth sensor based on coded aperture imaging capable of sensing other spacecraft in the formation
​[Ground] Integration of the estimation framework with the coded aperture sensor.

## Slide 3: SmoothNav Team
MIT
  Alvar Saenz-Otero Principal Investigator
  Danilo Roascio Post-doc / Lead
  William Sanchez Smoothing Estimation
  Antonio Teran Smoothing Estimation
JPL
  Carl Christian Liebe Co-I
  Norbert Sigrist Coded Aperture Optical Implementation
  Tim Setterfield Coded Aperture Algorithms / Calibration
Sponsor: STMD SSTP
Management: ARC

## Slide 4: SmoothNav Schedule
October 2016 1st Year of Project begins
August 2017 Payload Kickoff Meeting
October 2017 2nd Year of Project approved
November 2017 SmoothNav PIA signed
11 Dec 2017 1st ISS Test Session
31 Jan 2018 1st ISS Test Session (re-run)
02 Apr 2018 2nd ISS Test Session
Planned
Jul – Sep 2018 3rd – 4th ISS Test Sessions

## Slide 5: SmoothNav Status – Smoothing Algorithms
2nd ISS Test Session
Initial implementation of real time Smoothing Algorithms
  Implementation didn’t tolerate well the delayed/non-synchronous arrival of certain measurements
  Caused smoothing estimate to be (ironically) “less smooth” than Global Metrology (see right)
Factor graph was solved successfully in <1s time when run online on ISS satellites
Implementation is being improved in preparation for 3rd ISS Test Session
Data from VAS A was not downloaded and will have to be retrieved during the next test session
Global metrology estimate (top) vs. Smoothing estimate (bottom)

## Slide 6: SmoothNav Dependencies / Concerns
Dependencies
  Lots of ops in Summer 2018
Concerns
  Program ending Sep 2018

## Slide 7: Future
Re-SWARM
  Awaiting first test session
Gecko Skin w Airbus & TU Braunsweigh
  Prototype in Germany... will it be an AstroBee payload?
Use of Docking Ports with DLR in 2019
  Study in-space robotic assembly
  Would this be a need to make SPHERES Docking Port adapters so they can be used with AstroBee? (for "rigid" docking between satellites)