## Slide 1: Astrobee Status
SPHERES/Astrobee Working Group
October 3, 2018

## Slide 2: Technical Status: Integration
Free Flyer Cert Unit
  Temporary fix (motor isolator) allowed initial testing with the Cert Unit
  Propulsion module rework and reintegration with Cert Unit is nearly complete
Free Flyer Flight Unit
  2 core stacks complete and burnt-in
  3rd stack currently in burn-in
  Core harness assemblies nearly complete
Docking Station
  Completed builds of cert and 1st flight units
  Flight spare DC/DC board failed during qualification vibration testing. A replacement board is currently being integrated.
Ground Server
  Installed and ready for Operational Readiness Testing
DDS Server
  Primary machine received at MSFC
Cert Unit (Dock & Free Flyer) on granite table
Flight stack #3 burn-in

## Slide 3: Technical Status: Testing
Crew Control Station passed Payload Software Integration and Verification Facility (PSIVF) testing for Incr 59.
Completed risk reduction vibe of core stack and prop module.
Completed qualification vibe testing of the cert Dock, and acceptance vibe testing of Dock S/N 002.
Completed thermal testing of cert Dock.
Completed Joint Station LAN (JSL), Dock Power Quality, Dock EMI, flight Dock acoustic testing, and flight Dock human factors inspection at JSC.
Completed test of ground segment communications path from ARC through the Huntsville Operations Support Center (HOSC) at MSFC.
Successfully tested the REALM RFID Recon payload on the Free Flyer. The REALM payload flew the robot while searching for RFID tags.
Dock S/N 002 acceptance vibe test
Flight Dock S/N 002 in JSC EMI test chamber

## Slide 4: Administrator Demo Flight

## Slide 5: Technical Status: Safety
Completed Payload Safety Review Panel (PSRP) #3
  Discussed all open hazards
  Board approved most, pending final verification
  Board agreed we would try to close all remaining hazards out of board (i.e. no delta Phase 3)
On 5/9/2018, we met with a Payload Safety Review Panel (PSRP) splinter to discuss collision testing results. We received verbal approval to close our collision hazard. This means that, from a safety perspective, Astrobee will be allowed to operate autonomously.

## Slide 6: Technical Status: Operations
Docking Station S/N 002 was delivered to the Cargo Mission Contract (CMC) at JSC on 9/18/2018.
The Astrobee Mapping Activity, the first Astrobee ISS Ops activity, successfully occurred on 11/6/2017.
  This activity involved the crew completing camera and environmental calibration steps followed by the collection of a series of 14 panoramic photos in the JEM module.
Astrobee Robot Software released on 12/22/2017.
Astrobee received approval from JAXA for installation of the Docking Station in the Japanese Exploration Module (JEM).
We delivered a draft of the Dock installation procedure to Payload Operations. We are currently working to refine the procedure.
Part of JEM map with image poses

## Slide 7: PRACAs (Anomaly Reports)
ID | Title | Element | Status
1962 | Pink Poly Waiver | Free Flyer | OPEN
2052 | M211 Frame Holes | Free Flyer | CLOSED
2053 | Drive Shafts out of round | Free Flyer | CLOSED
2067 | 1st Article Inspection Reports received from outside Vendor for machined parts | Free Flyer | OPEN
2076 | Payload Connector Cutout | Free Flyer | CLOSED
2077 | M210 & M211 Payload Connector Cutout | Free Flyer | CLOSED
2086 | Dock AR Target Plate Corners | Dock | CLOSED
2114 | Propulsion Module Anomaly | Free Flyer | OPEN
2119 | Dock vibration qualification test - wire detached | Dock | CLOSED
2123 | Dock Heat Sink Screws | Dock | CLOSED
2129 | Dock Controller Board Malfunction | Dock | VERIFICATIONS COMPLETE
2130 | Dock Back Top Plate (M747-1) Bonding | Dock | VERIFICATIONS COMPLETE
2133 | Dock Fastener Bonding | Dock | VERIFICATIONS COMPLETE
2141 | EMI Non-Conformance | Dock | TIA Approved by EMEP
2144 | Dock SN003 DC-DC Board Failure After Vibe | Dock | VERIFICATIONS COMPLETE
PRACAs:
Green are latest changes