## Slide 1
Astrobee Payloads PIM Update

## Slide 2
Current Integration Work
  Gecko-Inspired Adhesive Grasping is targeting SpX-18 (07/08/19)
    Phase III Safety Review is scheduled on 3/28/19 (3-5 p.m. CT)
    Environmental testing (Acoustic and EMI/EMC) tentatively targeting early April (2nd week).
      EMI/EMC TRR – Scheduled for TBD.
    Hardware delivery scheduled for 5/9/19.
  SoundSee Mission is targeting SpX-18 (07/08/19)
    CDR was held 2/15/19 and H/W was design was approved to move forward.
    Phase II/III Safety was held on 2/27/19.
      Delta Phase III Safety Review to be scheduled once VTL items have been closed.
    Environmental testing (EMI/EMC) targeted for late April
    H/W delivery is scheduled for 5/9/19 – Pending no slips.
  Astrobatics software deploy is TBD
    Change form has been submitted to add Astrobatics to the Inc 59/60 research plan.
    Software deploy is still TBD.
  Zero Robotics is TBD

## Slide 3
In Work Flight Plan