## CoF Expenditures
CoF Costs Expenditures from FY 2021 through July-2026
Row Labels | Task Order | Title | FY21 | FY22 | FY23 | FY24 | FY25 | 2026 (thru Jul'26) | Total
105121 | 18F0538 | DEMOLITION OF FACILITIES | 483290.16 | 458183.35 | -1383.43 |  |  |  | 940090.08
105148 | 18F0536 | FP&D FEIF | 106652.73 | 2429.21 | -0.01 | 40119.75 |  |  | 149201.68
105379 | 18F0539 | FORTIFY SECURITY GATE |  | 39639 |  |  |  |  | 39639
105782 | 18F0548 | FORTIFY SECURITY GATES | 887276.65 | 772437.05 | 580.02 | -580.02 |  |  | 1659713.7
106107 | 18F0754 | T1723-24 OFFICE CONSOLID | 53913.5 | [5 empty] | 53913.5
106138 | 18F0556 | GARAGE PV | 266771.24 | 66444.16 | -7163.76 |  |  |  | 326051.64
106325 | 18F0558 | T1722 & T1723 | 941363.23 | 109239.46 | 63947.42 | 1186625.24 | 1186289.5 | 10166 | 3497630.85
106673 | 18F0671 | EMCS UPGRADE | 2215096.1 | 766242.03 | 1568692.4 | 1178781.17 | 1206173.13 | 335086.77 | 7270071.6
106675 | 18F0555 | LN2 TANK UPGRADE - DSGN | -823.65 | [5 empty] | -823.65
106899 | 18F0839 | REPAIR ELEVATORS | 8572.78 | 973388.88 | 196834.89 | 259810.75 | 210107.82 |  | 1648715.12
106900 | 18F0840 | LN2 TANKS | 20908.8 | 1932793.19 | 2028369.81 | 385816.89 | 240295.2 |  | 4608183.89
106902 | 18F0841 | REPAIR BANK 68 | 91196.78 | 567896.98 | 135713.1 | 13666.47 |  |  | 808473.33
107103 | 19F0065 | BLDG. 230 1ST & 2ND FLR | 3461.25 |  | -2235.65 |  |  |  | 1225.6
107167 | 19F0095 | DEMO MECH/ELEC ASSET |  | 106803.57 | 584334.94 | -121166.44 | 468742.53 |  | 1038714.6
107174 | 19F0099 | B183 SEISMIC BRACING | 125577.68 | 16157.25 |  |  |  |  | 141734.93
107175 |  | 16.5KV UNDRGRD CABLE |  |  |  | 53892.07 | 28329.12 | 69763.15 | 151984.34
107176 | 19F0097 | UNDERGROUND WATER |  | 9.28 | 383774.31 | 279023.14 | 22874.34 |  | 685681.07
107177 | 19F0098 | REPLACE SUBSTATION | 32848.83 | 37102.28 | 212935.08 | 72610.1 |  |  | 355496.29
107332 | 18F0536 | FEIF CONSTRUCTION | 3032097.2 | 26838475.27 | 34997315.3 | 7964099.87 | 2166131.55 | 0 | 74998119.19
107333 |  | DEMO BLDG 600 | 3324726.57 | [5 empty] | 3324726.57
107597 |  | B171 SEISMIC BRACING DESIGN |  | 76404.42 | 48518.04 | 19356.96 | 14366.3 |  | 158645.72
107672 | 21F0030 | B183 SEISMIC BRACING/CONST |  |  |  | 33197.6 | 45829.67 | 144099.31 | 223126.58
107719 |  | B230 REPLC MAIN ELCT SWTCHGRS |  |  | 39936.17 |  |  |  | 39936.17
107736 |  | DESIGN B170/B158 ELC BANKS |  | 178374.57 | 51461.77 |  |  |  | 229836.34
107834 | 22F0006 | REPLACE MAIN SUB-H |  |  | 3365408.64 | 7982391.56 | 29994 |  | 11377794.2
107907 | 22F0029 | INSTALL ELE. METERS - EUL |  |  | 63425.15 | 11284.28 |  | 26861.23 | 101570.66
108053 |  | SMART WATER INSTALLATION |  |  |  | 29179.26 | 6396.88 | 17955.2 | 53531.34
108123 |  | B171 SEISMIC BRACING |  |  |  | 410232.51 | 36746.89 |  | 446979.4
108218 | 23F0039 | INSTALL CRITICAL WATER METERS |  |  |  |  | 265347.67 | 24707 | 290054.67
108449 |  | TMO DEMO TM-15 |  |  |  | 10580.95 | 15602.2 | 234094.43 | 260277.58
108558 |  | UNDERGROUND CABLES |  |  |  |  | 1975914 | 2435247.88 | 4411161.88
108610 |  | WATER STORAGE TANKS |  |  |  |  | 94341.38 | 234254.19 | 328595.57
108671 |  | B180 SEISMIC STAIRS UPGRADE |  |  |  |  | 45781.8 | 1309.2 | 47091
108673 |  | FRC WEST LOT DEMO |  |  |  |  | 103434.34 | 128930.6 | 232364.94
108862 |  | FY25 TRAILER DEMO-DESIGN/CONST |  |  |  |  | 94060.99 | 1019682.11 | 1113743.1
109169 | 26F7021 | B230 SWITCHGEAR | [5 empty] | 8540.63 | 8540.63
Total |  |  | 11592929.85 | 32942019.95 | 43730464.19 | 19808922.11 | 8256759.31 | 4690697.7 | 121021793.11

## CoF Task Order Funding
Project Title | Task Order | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | Total | Comments
DEMOLITION OF FACILITIES | 18F0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 12/31/2022. Funds for this effort were provided in FY16-FY19 for this effort. No funds were provided in FY21 and beyond.
FP&D FEIF | 18F0536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 12/31/2025. Funds for this effort were provided in FY14-FY20 for this effort. No funds were provided in FY21 and beyond.
FORTIFY SECURITY GATE | 18F0539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 12/31/2022. Funds for this effort were provided in FY13 for this effort. No funds were provided in FY21 and beyond.
FORTIFY SECURITY GATES | 18F0548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 09/30/2023. Funds for this effort were provided in FY13 and FY17 for this effort. No funds were provided in FY21 and beyond.
T1723-24 OFFICE CONSOLID | 18F0754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 06/30/2022. Funds for this effort were provided in FY12-FY15 for this effort. No funds were provided in FY21 and beyond.
GARAGE PV | 18F0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 12/31/2022. Funds for this effort were provided in FY15-FY17 for this effort. No funds were provided in FY21 and beyond.
T1722 & T1723 | 18F0558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 09/30/2025. Funds for this effort were provided in FY16 for this effort. No funds were provided in FY21 and beyond.
EMCS UPGRADE | 18F0671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ends 12/31/2026. Funds for this effort were provided in FY17 for this effort. No funds were provided in FY21 and beyond.
LN2 TANK UPGRADE - DSGN | 18F0555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 03/31/2020. Funds for this effort were provided in FY15-FY17 for this effort. No funds were provided in FY21 and beyond.
REPAIR ELEVATORS | 18F0839 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
LN2 TANKS | 18F0840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 06/31/2025. Funds for this effort were provided in FY18 for this effort. No funds were provided in FY21 and beyond.
REPAIR BANK 68 | 18F0841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 12/31/2023. Funds for this effort were provided in FY18 for this effort. No funds were provided in FY21 and beyond.
BLDG. 230 1ST & 2ND FLR | 19F0065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 12/30/2020. Funds for this effort were provided in FY19 for this effort. No funds were provided in FY21 and beyond.
DEMO MECH/ELEC ASSET | 19F0095 | 0 | 0 | 0 | 531175 | 7600000 | 0 | 8131175
B183 SEISMIC BRACING | 19F0099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 09/01/2023. Funds for this effort were provided in FY19 for this effort. No funds were provided in FY21 and beyond.
CoF FP&D | 19F0096 | 0 | 0 | 248492 | 0 | 1054507 | 0 | 1302999
UNDERGROUND WATER | 19F0097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 03/30/2025. Funds for this effort were provided in FY19 for this effort. No funds were provided in FY21 and beyond.
REPLACE SUBSTATION | 19F0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PoP ended 12/31/2024. Funds for this effort were provided in FY19 for this effort. No funds were provided in FY21 and beyond.
B183 SEISMIC BRACING/CONST | 21F0030 | 7700000 | 9900000 | 5000000 | -1600000 | 0 | 2400000 | 23400000
REPLACE MAIN SUB-H | 22F0006 | 0 | 9300000 | 2100000 | 0 | 0 | 0 | 11400000
INSTALL ELE. METERS - EUL | 22F0029 | 0 | 125471 | 0 | 0 | 0 | 0 | 125471
INSTALL CRITICAL WATER METERS | 23F0039 | 0 | 0 | 440000 | 0 | 0 | 0 | 440000
B230 SWITCHGEAR | 26F7021 | 0 | 0 | 0 | 0 | 0 | 8000000 | 8000000
Total |  | 7900000 | 19325471 | 7788492 | -1068825 | 8654507 | 10400000 | 52999645