## Slide 1: The Geometry of Confidence
2026
New Mathematical Foundations for Joint Confidence Level (JCL) Analysis
By Aamir Ahmad, M.S. Applied Mathematics
Principal Consultant
at aamir.consulting
aamir.consulting
The Geometry of Confidence
Notes: Save questions for the end.
Worked at NASA’s Kennedy Space Center (KSC) with a background in applied mathematics.
I translate to unite:
Biologists -> Engineers
Statisticians -> Leadership
Math is a common language
I transform to create:
Earth Data -> Space Solutions
Historical Data -> Active Projects
Math is a structural common ground
Presentation today is inspired by my work on JCL analysis at KSC.

## Slide 2: Louis Fussell
The Geometry of Confidence
Louis Fussell’s 2024 presentation Standardization of JCL Value Selection
A JCL models the possible cost and schedule outcomes of a project through a Monte Carlo simulation based on initial schedule assumptions.
Louis wanted to develop a confidence interval around the perfect JCL point.
Why? To tie the JCL back to discussions about project risks
2026
Note: This is a photo of a French mathematician, not Louis Fussell.
aamir.consulting

## Slide 3: Part 1 The Basics of Joint Confidence Level (JCL) Analysis
The Geometry of Confidence
2026
aamir.consulting

## Slide 4: Archimedes’ Sun-Laser
Archimedes is a mathematician in Syracuse, Sicily
Roman ships are headed to siege the city
He will build a sun-laser to defend Syracuse.
Sun-Laser:
Subsystem 1: Mirrors to focus sun rays
Subsystem 2: A frame for mobility
2026
The Geometry of Confidence
aamir.consulting

## Slide 5: Establish Project Baselines
2026
The Geometry of Confidence
aamir.consulting
Notes: Design, build, test, and integration of the two subsystems.
Mainly NASA CEH with key substitutions
Lognormal distribution for uncertainties instead of triangular
Build up the JCL and point back to the risks
Risks A, B, C, D

## Slide 6: Run a Monte Carlo Simulation
2026
The Geometry of Confidence
aamir.consulting

## Slide 7: Flexible Thinking
Hmm…
Confidence intervals are STATISTICAL objects
Wait!
JCL distributions are PROBABILISTIC constructs
The devil’s in the details.
Confidence intervals have no meaning in this context.
2026
The Geometry of Confidence
The Doors.
No, the band.
The ?
aamir.consulting

## Slide 8: A New Data Table
While the Monte Carlo simulation is running, build a data table that records the
Individual risks (A, B, C, or D)
Risk combinations (e.g. A0C0)
that show up in each iteration of the scatter plot.
Then, report descriptive statistics of selected regions in the JCL.
This tells us the risk profiles that drive project performance to certain cost and schedule levels.
2026
The Geometry of Confidence
aamir.consulting

## Slide 9: Flexible Thinking
Hmm…
Confidence intervals are STATISTICAL objects
Wait!
JCL distributions are PROBABILISTIC constructs
A-ha!
We can report the statistics of TARGETED regions
The devil’s in the details.
Confidence intervals have no meaning in this context.
We get the best of both worlds.
2026
The Geometry of Confidence
aamir.consulting

## Slide 10: Part 2 Choosing Regions of the JCL to Compare
The Geometry of Confidence
2026
aamir.consulting

## Slide 11: Pick Two Points
We start by choosing two points on the JCL scatter pilot to compare and build the regions around
2026
The Geometry of Confidence
aamir.consulting

## Slide 12: Confidence Level Bands
Pro: All points are at a similar confidence level
Con: Different regions of the band are not comparable
2026
The Geometry of Confidence
aamir.consulting

## Slide 13: Elliptical Regions
Pro: Points in each region are statistically relevant to each other
Con: Points in the region are not at a similar confidence level
2026
The Geometry of Confidence
aamir.consulting

## Slide 14: The Best of Both Worlds
Pro: Points in each region are statistically relevant other and at a similar confidence level
Caution: Run enough interactions on the Monte Carlo simulation to reach convergence
2026
The Geometry of Confidence
aamir.consulting

## Slide 15: The Risk Vector
We have: The cost and schedule difference between the two points.
We need: To know which risks drive this difference.
2026
The Geometry of Confidence
aamir.consulting

## Slide 16: Part 3 Visualizing the Impacts of the Risks
The Geometry of Confidence
2026
aamir.consulting

## Slide 17
We can now see how each risk contributes to changes in cost and schedule and prioritize which ones need to be managed.
2026
The Geometry of Confidence
aamir.consulting

## Slide 18
We can now see how each risk combination contributes to changes in cost and schedule and prioritize which chains of risk need to be managed.
2026
The Geometry of Confidence
aamir.consulting

## Slide 19: The Risk Vector Revisited
A simple way to summarize which risks drove the difference between the two regions.
2026
The Geometry of Confidence
aamir.consulting

## Slide 20: Archimedes Moves On
Finishes building his sun-laser ahead of schedule and under budget
Turns his attention to moving the Earth with a lever and a fulcrum
2026
The Geometry of Confidence
aamir.consulting

## Slide 21: References
National Aeronautics and Space Administration. (2015). NASA Cost Estimating Handbook (Version 4.0). NASA Headquarters. https://www.nasa.gov/ocfo/ppc-corner/nasa-cost-estimating-handbook-ceh/
Fussell, Louis (2024, April 23). Standardization of JCL value selection [Conference presentation]. 2024 NASA Cost and Schedule Symposium, Hampton, VA, United States. https://www.nasa.gov/wp-content/uploads/2024/05/16-standardization-of-jcl-value-selection.pdf
2026
The Geometry of Confidence
aamir.consulting

## Slide 22: Contact
aamir.consulting@proton.me
https://www.linkedin.com/in/
aamir-consulting/
https://aamir.consulting/
Email
LinkedIn
Website
2026
The Geometry of Confidence
aamir.consulting