## Slide 1: Using Multiple Schedule Risk Analysis Runs to Drive Informed Decisions
2026 NASA COST & SCHEDULE SYMPOSIUM
Zachary Dolch
NASA Program Analysis & Control (PAAC) V Contract
Notes: Welcome and thank you. I'm Zachary Dolch from NASA.
Today I want to talk about something that many of us in the cost and schedule community are already doing informally - iterating through our Schedule Risk Analysis before we present results - and argue that we should be doing it deliberately, documenting every step, and presenting all of those results instead of collapsing them into a single output.
The goal is to change not necessarily how we run SRAs, but how we document and present them - and in doing so, make them significantly more useful for decision-making at all levels of the program.

## Slide 2: Agenda
SRA Fundamentals: What is an SRA, when is it used, and how it fits into NASA decision-making
The Multi-Run Approach: Concept, what to vary between runs, and how to structure the campaign
What the Ensemble Reveals: Sensitivity, trends, and the path from current posture to comfortable
Framing for Decision-Makers: Out-briefing the range and handling the single-number question
Lessons Learned & Key Takeaways

## Slide 3: What Is an SRA & Why It Matters
Not just a date - a probability distribution of outcomes based on what we know.
Update As Needed (e.g. rebaseline)
Update As Needed (e.g. rebaseline)
Risk-informed
(Element-level)
JCL (parametric or probabilistic)
Risk-informed
(Project-level)
Schedule
Risk
Analysis
(SRA / ICSRA / JCL)
Life Cycle Phases
Pre-Phase A
Phase A
Phase B
Phase C
Phase D
KDP-D
KDP-C
KDP-B
KDP-E
SRR
SDR/MDR
PDR
CDR
SIR
ORR
MRR/FRR
Baseline
Launch
MCR
KDP-A
Major Reviews
Life Cycle Gates
Major Events
A Schedule Risk Analysis (SRA) is a Monte Carlo simulation of the project schedule
Captures schedule uncertainty and risk that deterministic planning cannot reflect.
Produces a probability distribution of completion dates - not a single deterministic date
Results are expressed as confidence levels: P50, P70, P80, etc.
Required at key decision points: SRR, PDR, CDR, ORR, and annual reporting cycles
Driven requirements language.
Used internally by programs to assess posture, and externally for stakeholder/review board reporting.
Notes: The SRA is one of the most valuable tools in the schedule management toolkit precisely because it gives you a probabilistic view. You're not just saying "we'll be done on this date" - you're saying "here's the distribution of possible outcomes given what we know about our risks and uncertainties."

## Slide 4: What Gets Lost at the Out-Brief
Analysts already iterate - the analytical story disappears before anyone else sees it.
What analysts do during development
Run the initial SRA with first-pass inputs.
Examine results, spot questionable or uncertain inputs.
Adjust assumptions, re-run.
Consult with PMO or engineering on specific risks.
Continue iterating until results are coherent and defensible.
Your Tittle Here
What stakeholders see
A single P70 date.
One confidence distribution curve.
One set of inputs (if shared at all).
A pass or fail against an acceptance threshold.
What disappears between development and the out-brief
The sensitivity of the result to key risks and assumptions.
The range of plausible outcomes under different configurations.
The analytical story of what drove the result to where it landed.
The roadmap of what it would take to reach a more favorable number.
Notes: The iteration that happens during SRA development is NOT bad practice. It's actually good analytical hygiene. The problem is what happens to all that analytical work: it gets collapsed into a single presented output, and all the insight that was generated along the way never reaches the people who need it. Think about what you learn when you iterate. You learn which risks drive the result most. You learn how sensitive the P70 date is to changes in duration uncertainty. You learn what the schedule looks like if the most worrisome risk is retired. None of that information appears in the standard out-brief. The multi-run approach doesn't ask you to change how you develop the analysis. It asks you to start documenting the process you're already following, and to present the results of that process transparently instead of hiding them inside the final output.

## Slide 5: The Multi-Run Approach: Concept
You are not changing your process - you are changing how you document and present it.
Not About
Frequency
Deliberate Documentation
Configurations as Hypotheses
Journey as Output
The multi-run approach is not about running the model more times
Analysts already iterate during development - that's not new
It's about making those iterations deliberate, documented, and part of the presentation
Each run configuration = a different set of documented analytical assumptions
Each configuration represents a different analytical hypothesis about the project's risk posture
Running N configurations produces N data points that together describe schedule sensitivity
The key shift: from hiding the analytical journey to making it the output
Notes: You're already doing this work. You're already iterating. You're already discovering sensitivity and exploring scenarios. The only thing that's changing is that instead of that work disappearing when you produce the final output, it becomes part of the record. The adoption barrier is lower than it might seem, because the core analytical process doesn't change. What changes is documentation discipline and how you structure the out-brief.

## Slide 6: What to Vary Between Runs
Risk Likelihood (%)
Risk Impact
Duration Uncertainty Ranges
Scope & Programmatic Assumptions
Risk Mitigation Scenarios
Fully Mitigated Reference Run
Adjust probability of occurrence for individual identified risks
Tighten or widen optimistic/pessimistic bounds on activity durations
Reflect known scope decisions, resource changes, or schedule recovery actions
Vary schedule consequence (duration) if a risk materializes
Model the effect of retiring or partially mitigating specific risks
All current risks retired - establishes the theoretical best-case as an anchor
Vary inputs with high uncertainty AND high stakeholder interest - not just what's easy to change.
Notes: Not every run needs to vary all of these parameters - and in fact, varying too many things at once makes interpretation harder. The most analytically useful runs are those where you vary one or two meaningful inputs and can directly attribute the change in the result to those inputs. The fully mitigated run is particularly valuable because it answers a question that programs often can't answer otherwise: "What would our schedule look like if everything we're worried about goes away?" That's a meaningful data point for leadership.

## Slide 7: Process: Structuring the Campaign
A structured analytical campaign - each step deliberate, documented, and defensible.
1
5
2
3
4
6
7
Initial consultation with PMO
Map risks, establish likelihood %, impact, and duration uncertainty inputs
Configure and run the baseline SRA
Document results as Run 1 - this is your starting point for all comparisons
Out-brief: walk through each run in sequence
Present the analytical journey, the trend, and what it means for program decisions
Summarize results
AI-assisted summarization of run documentation can accelerate this step - review and revise carefully
Repeat for each analytical scenario
Continue until you've covered the scenarios that matter most for the program's decisions
Update inputs → rerun → document
Record parameters changed, rationale, and output results for this run
Define the next hypothesis
Decide what you're testing: what changes, and why - document rationale before running
(critical step that prevents post-hoc rationalization of results)

## Slide 8: Configuration Documentation: The Critical Discipline
For each run, record:
  Input parameters changed - which fields, old value → new value
  Rationale - new data from engineering? Team discussion outcome? Programmatic decision made?
  Output results - P50, P70, P80 completion dates
  Key observations - what did this run reveal that the previous run didn’t?
Why this discipline matters:
  Notes become the record that makes the summary briefing coherent and defensible
  Enables full traceability: anyone can follow the analytical logic from first run to final recommendation
  Transforms the out-brief from an assertion into a presentation of documented evidence
  Allows the analyst to stand behind the recommendation with confidence
Document not just what changed - document WHY.
Run 3
MPP Rev 3
Used Rev 3 schedule file
Ran 5,000 iterations
Schedule correlation at 0.3
Reduced FLT duration uncertainties
Run 0
MPP Rev 1
Set baseline
Duration correlation set to 0.5
FSM set to Constant 0d
Original SRA configuration
Run 1
MPP Rev 1
Used Rev 1 schedule
Ran 5,000 iterations
Run 2
MPP Rev 2
Used Rev 2 schedule file
Ran 5,000 iterations
Reduced schedule correlation from 0.5 to 0.3
Run 4
MPP Rev 4
Used Rev 4 file
Ran 5,000 iterations
Reduced I&T duration uncertainties
Notes: This is the foundational discipline of the entire approach. It's easy to say "I'll document it later" and then never do it with the same fidelity as doing it in real time. Practical advice: keep the run log open in a separate window while you're working in the SRA tool. Before you make any change to the inputs, write down what you're changing and why. After you run, write down the key output numbers and what they reveal.

## Slide 9: Sensitivity Analysis in Action
The ensemble of runs answers questions that a single run cannot:
How sensitive is the P70 date to the highest-impact risks?
  Model each high-impact risk independently - retire it in one run, keep it in another
What does the schedule look like under current posture vs. fully mitigated?
  Compare the baseline run to the fully-mitigated reference run
How much does the result shift as uncertainty ranges are refined?
  Tighten duration bounds in successive runs as engineering data matures
Which programmatic decisions move the outcome most?
  Model scope changes, resource additions, or schedule recovery separately
Not just reporting a problem - providing a quantitative basis for the solution.
Probability %
Finish Date
P70
NOV 2028
DEC 2028
JAN 2029
FEB 2029
4
3
2
1
Notes: This is where the multi-run approach starts delivering its analytical value. Each row here maps directly to a set of run configurations - these aren't abstract questions, they're things you can answer definitively with your run log in hand. When you present this to a review board, you can point to specific runs: "We found that retiring Risk A moves the P70 date by approximately 3 weeks. Retiring Risk B moves it by 6 weeks. Combined, those two actions get us to a P70 date inside the current baseline." That's a fundamentally different conversation than "our P70 date is past our baseline, here's why." You're not just reporting a problem - you're providing a quantitative basis for the solution.

## Slide 10: From Point Estimate to Trend
Plot P50, P70, and P80 completion dates across all runs, aligned with configuration notes
  Transforms the SRA from a single data point into a trend that leadership can directly engage with
Shows direction of travel: are conditions improving or degrading across configurations?
  Each data point has a documented rationale - reviewers can interrogate any specific run
The trend chart is the primary artifact that makes the multi-run approach visible to decision-makers
A productive conversation, not a defense of a black-box number
SRA
RUN
#1
P50 Date
NOV 2028
P70 Date
FEB 2029
APR 2029
P80 Date
P70 DATE
2/9/29
SRA
RUN
#2
P50 Date
DEC 2028
P70 Date
JAN 2029
FEB 2029
P80 Date
P70 DATE
1/31/29
SRA
RUN
#3
P50 Date
OCT 2028
P70 Date
DEC 2028
JAN 2029
P80 Date
P70 DATE
12/15/28
SRA
RUN
#4
P50 Date
OCT 2028
P70 Date
NOV 2028
NOV 2028
P80 Date
P70 DATE
11/14/28
Notes: This is the chart that you bring to the review board as your primary SRA output. What leadership can immediately read from this chart: - Is the schedule getting better or worse as we refine our analysis? - How much does the result move when we change specific assumptions? - Where is the "floor" - what does the schedule look like under the most optimistic defensible assumptions? - Where is the "ceiling" - what does it look like under current risk posture? The beauty of this presentation format is that it invites engagement. Leadership can ask "what happened between run 3 and run 4?" and you can point directly to the run log and explain. That's a productive conversation - not a defense of a black-box number.

## Slide 11: The Story the Ensemble Tells: The Path to Comfortable
The ensemble doesn't just describe where you are - it maps the path to where you need to be
  Specific runs model: risk retirement, schedule recovery, scope relief, mitigation adoption
The gap between current posture and fully-mitigated posture is quantified and visible
  Leadership can see not just a result, but what specific actions close the gap
This answers the question that programs actually need to answer: "What do we need to do?"
  The range of SRA results becomes a roadmap, not just a report card
The ensemble answers 'what do we need to do?' - not just 'where are we?'
11/14/28
P70 Date
Delivery Date
Confidence
Deltas from
Run #1
Reduced I&T duration uncertainty.
72%
87d | +20%
Run #4
12/15/28
P70 Date
Delivery Date
Confidence
Deltas from
Run #1
Reduced FLT duration uncertainties.
61%
56d | +9%
Run #3
1/31/29
P70 Date
Delivery Date
Confidence
Deltas from
Run #1
Reduced schedule correlation.
49%
9d | -3%
Run #2
2/9/29
P70 Date
Delivery Date
Confidence
Deltas from
Run #1
Original configuration.
52%
-----
Run #1
Notes: This is the most actionable slide in the deck, particularly for program managers. The key shift here is from the SRA as a diagnostic tool ("here's our schedule posture") to the SRA as a prescriptive tool ("here's what we need to do to improve our schedule posture"). The fully-mitigated reference run is essential for this conversation. This is also how you use an SRA result that doesn't meet acceptance thresholds productively. Instead of "we didn't pass," you're saying: "The current posture gives us P70 at Date A. Here's what we've modeled about what it takes to get to an acceptable result. Here are the specific actions and their modeled schedule impact." That's a conversation leadership can engage with and act on.

## Slide 12: Reframing the Conversation: Not a Verdict
When the analytical process is visible, quality - not just the number - is what gets evaluated.
THE OLD FRAMING
"Did we pass?“
Binary pass/fail judgment against a threshold
A single P70 date is the answer
If the date doesn't meet expectations: program has failed the SRA
Leads to defending a number rather than understanding posture
Creates an incentive to present the most favorable result rather than the most honest analysis
THE NEW FRAMING
"What is the model reflecting?“
What assumptions drove this result?
Are those assumptions well-calibrated?
What specific actions would move the result in a favorable direction?
The multi-run record already has those answers - you modeled them
Full analytical transparency shifts the evaluation from "did you pass?" to "is your analysis sound?"
Notes: When SRA inputs are clearly characterized, the result at any confidence level is best understood as an analytically grounded starting point for discussion - not a final judgment.

## Slide 13: Out-Briefing the Range
Structure the out-brief as a journey, not a report of a final number.
SET THE STAGE
"Here's what we set out to analyze, and here are the parameters we started with."
WALK EACH RUN IN SEQUENCE
For each run: what changed, why we changed it, and what the result showed us.
PRESENT THE TREND
The run-by-run chart: P70 dates across configurations, with configuration notes visible.
KEY SENSITIVITIES
Which inputs moved the result most? Which risks or decisions are the dominant drivers?
STATE THE PATH FORWARD
"Here's where we are. Here's what the model shows it takes to reach a comfortable posture."
Notes: This structure works for presentations to review boards, program leadership, or stakeholder groups. The key principle is that the out-brief tells a story - the analytical journey from first assumptions to final recommendation.

## Slide 14: Handling "What's Your Number?"
Anchor to the most analytically defensible run, then contextualize with the range.
The expectation of a single P70 date is not going away - and it shouldn’t
Programs and review boards need a point of reference for decision-making; the multi-run approach does not eliminate that need.
The most defensible run is not necessarily the one with the best-looking result - it's the run whose inputs you're most confident in. The documented campaign makes that distinction explicit.
Language that works:
"Our best-supported result is [P70 date] under [clearly documented assumptions]. The range across our configurations is [X] to [Y], driven primarily by [key variables]. The assumptions behind our primary result are [X, Y, Z], and here's our confidence in each."
The documented run campaign earns your right to present a recommendation with analytical confidence.
You are not hiding the single number - you are presenting it with the rigor it deserves.
Notes: This slide addresses the most common practical concern analysts have when they hear about the multi-run approach: "But stakeholders want a number. I can't walk in and show them a chart." The answer is: you still give them a number. You just present it better. The difference is that instead of saying "P70 is Date X" and hoping nobody asks too many questions, you're saying "P70 is Date X under these specific, documented assumptions, and here's what the result looks like when those assumptions change." That's a much stronger position to be in. The "most analytically defensible run" framing is useful: it's not necessarily the run with the best-looking result. It's the run whose inputs you're most confident in. That distinction matters - and it's one the multi-run approach makes visible, because you've documented why you made every assumption. If a reviewer pushes back on your primary result, the run log is your evidence. "We considered that assumption - here's run 3, where we used the more conservative value, and here's what it produced." That's a different conversation than trying to defend a number whose origins aren't fully visible.

## Slide 15: Lessons Learned
Start documentation from run 1 - retrofitting notes at the end is painful and incomplete.
  The discipline of real-time documentation pays off disproportionately at the out-brief stage.
AI-assisted summarization of run notes can meaningfully reduce summary preparation time - but requires careful review.
Calibrate depth to the audience: review boards need the story; technical peers can engage with every run.
Always include a fully-mitigated reference run - it anchors the range and makes the gap visible and discussable.
The multi-run approach does not eliminate subjectivity - it makes subjectivity visible, documented, and discussable.
Time investment: incremental over a single-run campaign, with a high return in the quality and credibility of the out-brief.
  Practical number of runs - enough to demonstrate sensitivity without making the out-brief unwieldy.
Document from run 1, present the range, calibrate your depth to the audience.

## Slide 16: Key Takeaways
You're already iterating - start making those iterations visible and documented
Document not just what changed, but why - the rationale is what makes the record defensible
Present the range, not just the endpoint - the trend tells the story a single number can’t
The ensemble answers: "What does it take to get comfortable?" - that's what leadership needs
An SRA result that doesn't meet expectations is not a verdict - it's the beginning of a productive conversation

## Slide 17
Questions?