## Slide 1: Where it All Breaks Down: How Cost Growth Exists Within Specific WBS Elements
Zachary Matheson – Zachary.matheson@nnsa.doe.gov
Vikram Basude – Vikram.basude@nnsa.doe.gov

## Slide 2
Zachary Matheson
OPERATIONS RESEARCH ANALYST, NNSA
Zachary is an analyst in the National Nuclear Security Administration (NNSA) Office of Programming, Analysis, and Evaluation (PA&E).
Vikram Basude
Senior Associate, Technomics, Inc.
Vikram supports the NNSA at the Office of Programming, Analysis, and Evaluation (PA&E) and the Navy at PEO IWS (Program Executive Office Integrated Warfare Systems)
Meet your Speakers

## Slide 3
Problem/Background
Data Collection, Normalization, and Validation & Verification
Cost Growth Analysis
New/Future Capabilities
01
02
03
04
Agenda

## Slide 4
PROBLEM
NNSA capital projects face persistent cost growth, limited visibility into lower-level drivers due to inconsistent WBS structures, and re-baselining that can mask cumulative performance degradation in top-level EVM metrics.
APPROACH
Leverage Normalized Earned Value Management (EVM) Work Breakdown Structures (WBS) with re-defined metrics to identify, quantify, and benchmark baseline deviation drivers across projects.
OBJECTIVE
Identify which lower-level elements drive baseline deviation, quantify the associated cost, schedule, and scope impacts, and demonstrate how WBS-level insights can improve estimating, benchmarking, and mitigation strategies.
Problem/Background

## Slide 5: Data Collection, Normalization, and Validation & Verification

## Slide 6
Data
Collection
1
Used a DOE system (PARS) used for tracking, assessing, and reporting on the status and performance of projects
Data processing and data wrangling
Outcomes
  Manufacturer and Operating (M&O) WBS
  Time-phased costs by WBS
  Project Documents
Normalization
2
Standardized M&O WBS & escalated project costs
  Leveraged Machine Learning model to standardize at scale
  Used Python script to escalate costs
  Set thresholds to ensure projects were capturing 95% of cost growth
V&V
3
Performed a Qualitative and Quantitative Validation and Verification
  Trustworthy dataset - ensure no AI hallucinations

## Slide 7
WBS Variations Across Projects Are Inconsistent
Project One | Level
project management | 2
Project Office | 3
Project Three | Level
project management | 2
03.01.14 project management | 3
Project Two | Level
project integration | 2
construction project management | 3
Title | Level
TOTAL PROJECT COST | 1
Total Estimated Cost | 2
Management and Support | 3
Design and Non-Recurring Engineering | 3
Site Work | 3
Vertical Construction | 3
Standard Equipment & Utilities | 3
Process Equipment & Instrumentation | 3
Transition and Turnover to Operations | 3
Other Project Costs | 2
Pre-CD-1 Costs | 3
Post-CD-1 Costs | 3
Other Direct Costs | 2
Contractor Fee | 2
Capital Acquisition Estimating Framework 2.0
  Uses UNIFORMATII & Masterformat
  Developed by CEAG (Cost Estimating Analysis Group)
    Cross-functional group encompassing LPSs & HQ
  Allows a way for M&Os to bucket their costs in a standardized format
Notes: Background on CAEF 2.0: CEWG – Cost Estimating Working Group developed a standardized WBS LPS can utilize to track/report their project costs.

## Slide 8
AI/ML Solution
For more details on the model, refer to 2023 CECOP Presentation All in the Hierarchy: Meta-Estimators for Work Breakdown Structures by Maura Lapoff & Patrick Shelton
What is it?
A tool that reads text, interprets meaning, and classifies it into a predefined category
Output
CAEF 2.0 standard WBS for each historic WBS
Scope of data
All Active and Completed NNSA projects
Limitations
Limited sample size and lack of contextual information
Natural Language
Processing
(NLP) Model
ENGINE

## Slide 9
Perform validity checks on each lowest level WBS element
Perform manual re-allocation
Inconsistent or incorrect outputs
Unknown acronyms
Context specific or niche WBSs
Retain Output
Qualitative Checks
Identify and compare ACWP to the Total Cost in closeout report
Split project cost categories from ACWP
Compare to Actual Closeout reports
Re-Bucketing WBS elements to align with Reported Costs
Input: Qualitative checked WBS
Pass/Fail QA
Investigate Omission from Results
Pass
Fail
Maintain quantitative project category split
Qualitative & Quantitative V&V Process Flow

## Slide 10
Total number of WBS elements
High-Level Elements
Low-Level WBS Elements
92%
55%
19,291
Accuracy Percentage of WBS Levels
Project Context
Legacy Acronyms
Scope Nuances
Niche WBS Elements
Observed limitations
QA Findings
ML Model
WBS
Includes all corrections and assumptions from historical projects
All projects WBS standardized to CAEF 2.0
New training dataset
V&V Process
Key Improvements:
Ability to more accurately output standardized WBSs & close the gap on key limitations

## Slide 11: Cost Growth Analysis

## Slide 12
Metric | Completed projects | Active projects
Cost deviation |  | 
Scope deviation |  | 
Schedule deviation |  | 
Metric | Completed projects | Active projects
Cost deviation |  | 
Scope deviation |  | 
Schedule deviation |  | 
Intended to show deviations from the original project baseline, not the most recent re-baseline
Metrics are evaluated for each project at WBS level 3
Cost Growth Metrics
Notes: Why different metrics for active vs completed projects? If a project never rebaselines, then the two metrics would ideally be the same. But rebaselines do happen, so out metrics intend to isolate specific types of growth behaviors independently of one another
Take cost growth for instance. Makes sense for completed projects: how much you actually spent vs how much you originally expected to spend. But scope changes make it difficult to use that same metric for active projects – for example, consider a project that completed half its original scope at double the expected cost.

## Slide 13
Both active and completed projects experience cost inefficiency
  Metrics suggest higher inefficiency for completed projects across most WBS elements, however…
  Discrepancy is likely related to different metrics for active vs. completed projects
Favorable cost deviation for transition to operations (TTO) for completed projects may be a sign that TTO scope is trimmed to be completed off-project
Chart: Cost Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, completed | 0.25342 | 0.19649 | -0.63311 | 0.46993 | 0.16645 | 0.20049 | 0.50964 | 0.39659
Avg, active | 0.058016 | -0.010614 | -0.0125 | -0.11333 | 0.1386 | 0.031945 | 0.11173 | 0.02316
Cost Deviation Metrics
Numbers indicate # of projects
← Better than expected | Worse than expected→

## Slide 14
Non-rebaselined projects experienced greater design and engineering cost inefficiency than projects which rebaselined
Otherwise, rebaselined projects show consistently greater cost inefficiency for nearly all WBS tasks than projects which have not been re-baselined
Particularly pronounced for WBS elements that take place “in the field” rather than behind a desk, including
  site work
  equipment procurement and installation
  vertical construction
  transition to operations
Chart: Cost Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, rebaselined | 0.15604 | 0.094907 | -0.030396 | 0.24631 | 0.19034 | 0.24253 | 0.32472 | 0.11976
Avg, not rebaselined | 0.10638 | 0.038206 | -0.36339 | -0.054934 | 0.088836 | -0.11539 | -0.12935 | 0.22271
Cost Deviation Metrics
Numbers indicate # of projects
← Better than expected | Worse than expected→

## Slide 15
Large schedule deviations for standard and process equipment are each due to a single outlier project
As suggested before, TTO for completed projects shows evidence of cut scope
Minor scope creep elsewhere, with no clear difference between completed vs incomplete projects
Chart: Scope Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, completed | 0.18021 | 0.1375 | -0.38689 | 0.32537 | 0.11498 | 0.14913 | 0.40201 | 0.29818
Avg, active | 0.13415 | 0.23158 | 0.00318 | -0.040003 | 2.9791 | 0.81139 | 0.31556 | 0.066233
Scope Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→
Notes: Emphasize that TTO scope cutting could be good or bad

## Slide 16
Rebaselined projects see scope growth in every category
  Scope discovery is a common cause for project re-baselines.
Non-rebaselined categories mostly appear to have had scope cut
  Perhaps scope was shed to complete within baseline
  Minor design and engineering scope added to non-rebaselined projects
Chart: Scope Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, rebaselined | 0.25489 | 0.33053 | 0.11117 | 0.18222 | 3.106 | 1.014 | 0.46557 | 0.18245
Avg, not rebaselined | -0.00090708 | -0.010936 | -0.36045 | -0.063522 | -0.075387 | -0.15484 | 0.002002 | 0.088982
Scope Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→

## Slide 17
Completed projects show almost no schedule delays outside of TTO
  Not dependent on the choice of metric; using the active project metric of BCWP/BCWS yields a similar number
May be an artifact of the type of projects in NNSA’s portfolio
  Older projects tended to be smaller, less complex, less expensive, and therefore less prone to delays than today’s active projects
Chart: Schedule Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, completed | 0.036233 | 0.041499 | 0.51813 | 0.024056 | 0.066093 | 0.057275 | -0.0068927 | -0.010812
Avg, active | 0.49733 | 0.60056 | 3.6968 | 1.1541 | 0.74925 | 0.69771 | 0.4221 | 0.27305
Schedule Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→

## Slide 18
On average, no part of a project completes on or ahead of schedule
Later project phases (which appear toward the bottom) tend to have increasingly longer delays
Chart: Schedule Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, rebaselined | 0.33834 | 0.33593 | 4.1525 | 0.58714 | 0.54277 | 0.61449 | 0.30103 | 0.08721
Avg, not rebaselined | 0.27471 | 0.43843 | 1.2427 | 0.78123 | 0.37582 | 0.18211 | 0.3563 | 0.3237
Schedule Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→

## Slide 19
Did a sensitivity analysis with data acceptance criteria
  Any effects of the data cutoff threshold, if they exist, are overshadowed by the effects of influential points in a small dataset
Influential points
  Using the metrics we’ve defined, project activities with small baselines can have an outsized influence on aggregate score even if the actual change in dollars is small
Consider using weighted average or median rather than flat average
  See backups
Lessons Learned

## Slide 20: Conclusions and Future Work

## Slide 21
Cost, Schedule, & Phasing Estimating Relationships
Developing PER of when WBS occur throughout the lifecycle of a project
Ability to accurately, efficiently, and confidently perform…
Create XERs
Utilizing Baseline Growth Factors at the WBS level to forecast and assess projects with increased granularity
Lower-Level EVM Project Control
Our baseline growth defined metrics can allow organizations to detect cost or schedule risks sooner and take corrective action before they escalate.
Early Warning Systems
New/Future Capabilities
Organizations which implement these steps will be well-positioned to better quantify cost growth risks, identify mitigation strategies, and ultimately support more informed mission execution

## Slide 22: Questions

## Slide 23: Additional Material

## Slide 24: Snapshot of CAEF WBS
Full WBS - Levels 0-9

## Slide 25: Back Up

## Slide 26: WBS Benchmarking Capability

## Slide 27
Benchmarking and Cost Growth
What are benchmarking tools?
Benchmarking tools are a way to quickly compare project cost estimates to historical actual costs for similar projects
How does benchmarking combat baseline growth?
Ensure the best estimate is put forward as the baseline and removing unrealistic estimates
With project EVM data mapped to a common WBS, we can benchmark projects at lower levels than before

## Slide 28
Capital Acquisitions Analytic Toolkit (CAAT)
Has suite of tools for benchmarking capital projects at lower WBS levels
Ability to export data and create XERs
Will develop tools for generating common visualizations, including benchmarks during Datathon Group 5
CAAT – WBS Benchmarking
PA&E Benchmarking Tools

## Slide 29
PARS Data Selection
1
Project Inclusion
Identify Active and Completed Projects
SPAE Report
SPAE (bcwS, bcwP, Acwp, Etc) files in Reports
M&O WBS
EVM data provides time-phased Actual Cost of Work Performed (ACWP) through M&O WBS
2
3
PARS
A DOE system used for tracking, assessing, and reporting on the status and performance of projects
Includes Project Documents and WBS level data
Project Assessment and Reporting System
Objective
Obtain Managing and Operating (M&O) WBS & associated costs

## Slide 30
Multi-Year SPAE WBS Normalization
Set Thresholds
Multi-Year SPAE
Data Sync
Visualize Baseline Over-Time
The SPAE File in PARS only gives EVM metrics on the most recent baseline. To assess baseline deviation, we needed all prior baselines.
Pars Request
Set Thresholds
Data Sync
Requested and received Multi-Year SPAE File from PARS
Excluded projects where initial baseline differed from our earliest baseline in dataset by more than 5%
Leveraged a Python script to escalate EVM dollars and apply WBS V&V across multi-year SPAE WBSs.
V&V WBS
Notes: Special request to PARS
5% thresholds for analysis in the case of incomplete EV data
95% of post baseline execution
Utilized Python Script to sync the WBS reallocation mapping and aggregation to level 3 WBS

## Slide 31: Cost Growth Results
Using median rather than mean

## Slide 32
When using the median instead of the mean:
  Slight positive cost deviation observed for standard equipment vanishes
  Slight negative cost deviation observed for vertical construction for active projects vanishes
Both active and completed projects experience cost inefficiency
  Metrics suggest higher inefficiency for completed projects across most WBS elements, however…
  Discrepancy is likely related to different metrics for active vs. completed projects
Favorable cost deviation for transition to operations (TTO) for completed projects may be a sign that TTO scope is trimmed to be completed off-project
Cost Deviation Metrics
Numbers indicate # of projects
← Better than expected | Worse than expected→
Chart: Cost Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, completed | 0.34747 | 0.21237 | -0.77581 | 0.59502 | 0.28827 | -0.018029 | 0.62568 | 0.36515
Avg, active | 0.038701 | 0.0072894 | -0.0022751 | 0.0068441 | 0.095651 | 0.012858 | 0.085697 | 0.017764

## Slide 33
Median cost inefficiency for site work for non-rebaselined projects is positive, while mean is negative. Otherwise, no major changes
Non-rebaselined projects experienced greater design and engineering cost inefficiency than projects which rebaselined
Otherwise, rebaselined projects show consistently greater cost inefficiency for nearly all WBS tasks than projects which have not been re-baselined
Particularly pronounced for WBS elements that take place “in the field” rather than behind a desk, including
  site work
  equipment procurement and installation
  vertical construction
  transition to operations
Cost Deviation Metrics
Numbers indicate # of projects
← Better than expected | Worse than expected→
Chart: Cost Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, rebaselined | 0.06819 | 0.025424 | -0.0022751 | 0.074609 | 0.13522 | 0.065896 | 0.13953 | 0.031751
Avg, not rebaselined | 0.043455 | 0.081155 | -0.24907 | -0.029421 | 0.12315 | -0.12064 | 0.097746 | 0.18432

## Slide 34
No meaningful differences between mean and median
Large schedule deviations for standard and process equipment disappear when using median rather than mean
As suggested before, TTO for completed projects shows evidence of cut scope
Minor scope creep elsewhere, with no clear difference between completed vs incomplete projects
Scope Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→
Chart: Scope Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, completed | 0.26083 | 0.15571 | -0.63463 | 0.38915 | 0.21021 | 0.0095451 | 0.45631 | 0.25
Avg, active | 0.12476 | 0.30638 | 0.096394 | 0.019678 | 0.10079 | 0.41155 | 0.26553 | 0.15203
Notes: Emphasize that TTO scope cutting could be good or bad

## Slide 35
Rebaselined projects see scope growth in every category
  Scope discovery is a common cause for project re-baselines.
Non-rebaselined categories mostly appear to have had scope cut
  Perhaps scope was shed to complete within baseline
  Minor design and engineering and site work scope added to non-rebaselined projects
Scope Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→
Chart: Scope Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, rebaselined | 0.27659 | 0.47405 | 0.2592 | 0.1274 | 0.16957 | 0.5512 | 0.41526 | 0.18773
Avg, not rebaselined | -0.081335 | -0.043621 | -0.40583 | -0.16684 | -0.15356 | -0.187 | 0.27319 | 0.071256

## Slide 36
No meaningful differences between mean and median
Completed projects show almost no schedule delays outside of TTO
  Not dependent on the choice of metric; using the active project metric of BCWP/BCWS yields a similar number
May be an artifact of the type of projects in NNSA’s portfolio
  Older projects tended to be smaller, less complex, less expensive, and therefore less prone to delays than today’s active projects
Schedule Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→
Chart: Schedule Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, completed | 0.024722 | 0.021981 | 0.060811 | 0.0133 | 0.060345 | 0.10161 | 0 | 0.014493
Avg, active | 0.72248 | 0.47095 | 1.9817 | 0.94267 | 0.2548 | 0.52483 | 0.24606 | 0.15821

## Slide 37
No meaningful differences between mean and median
On average, no part of a project completes on or ahead of schedule
Later project phases (which appear toward the bottom) tend to have increasingly longer delays
Schedule Deviation
Numbers indicate # of projects
← Better than expected | Worse than expected→
Chart: Schedule Deviation
| Overall | MANAGEMENT-AND-SUPPORT | TRANSITION-AND-TURNOVER-TO-OPERATIONS | VERTICAL-CONSTRUCTION | PROCESS-EQUIPMENT-&-INSTRUMENTATION | STANDARD-EQUIPMENT-&-UTILITIES | SITE-WORK | DESIGN-AND-NON-RECURRING-ENGINEERING
Avg, rebaselined | 0.19799 | 0.32919 | 1.9817 | 0.072845 | 0.22488 | 0.45896 | 0.20785 | 0.0585
Avg, not rebaselined | 0.09806 | 0.14574 | 1.3009 | 0.11321 | 0.13279 | 0.16411 | 0.25006 | 0.051724